## Manual Chart
Winter 25-26' CSULB Drone Engineering Cohort
December 10th, 2025 thru January 20th, 2026
| TASK NAME | Deliverable | START DATE | END DATE | DURATION | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 : 11/3- 11/9 | [6 empty] | WEEK 2: 11/10 - 11/16 | [6 empty] | WEEK 3: 11/17 - 11/23 | [6 empty] | WEEK 4: 11/24 - 11/30 | [6 empty] | WEEK 5: 12/1 - 12/7 | [6 empty] | WEEK 6: 12/8 - 12/14 | [6 empty] | WEEK 7: 12/15 - 12/21
[8 empty] | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su
Pre Planning
| Working Agreements & Recruiting | Assigning Task Ownership | 2025-11-03 | 2025-12-19 | 47 | Everyone | 50%
| Block Diagrams & System Context | Master System Diagram.png v1.0 | 2025-11-24 | 2025-12-07 | 14 | Everyone | 0% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T; WEEK 4: 11/24 - 11/30 M to WEEK 5: 12/1 - 12/7 Su
| Main Part Shortlists | Main Parts Shortlist.xls v1.0 | 2025-12-01 | 2025-12-14 | 14 | Everyone | 0% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T; WEEK 5: 12/1 - 12/7 M to WEEK 6: 12/8 - 12/14 Su
| Main Part Trade Studies | Main Part Trade Studies .xls v1.0 | 2025-12-01 | 2025-12-14 | 14 | Everyone | 0% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T; WEEK 5: 12/1 - 12/7 M to WEEK 6: 12/8 - 12/14 Su
| Interface Control Draft | ICD.txt v1.0 | 2025-12-08 | 2025-12-21 | 14 | Everyone | 0% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T; WEEK 6: 12/8 - 12/14 M to WEEK 7: 12/15 - 12/21 Su
| Test Plan Outline + Bringup Checklists | Test Plan.txt & Bringup Checklist.txt v1.0 | 2025-12-08 | 2025-12-21 | 14 | Everyone | 0% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T; WEEK 6: 12/8 - 12/14 M to WEEK 7: 12/15 - 12/21 Su
mCAD
|  |  | 2018-01-05 | 2018-01-08 | TBD | Everyone | 0% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T
|  |  | 2018-01-05 | 2018-01-08 | TBD | Everyone | 0% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T
|  |  | 2018-01-11 | 2018-01-16 | TBD | Everyone | 0% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T
|  |  | 2018-01-14 | 2018-01-19 | TBD | Everyone | 0% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T
|  |  | 2018-01-17 | 2018-01-21 | TBD | Everyone | 0% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T
|  |  | 2018-01-20 | 2018-01-23 | TBD | Everyone | 0% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T
eCAD Flight Controller
|  |  | 2018-02-05 | 2018-02-08 | TBD | Bao | 0% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T
|  |  | 2018-02-08 | 2018-02-13 | TBD | Bao | 0% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T
|  |  | 2018-02-11 | 2018-02-16 | TBD | Bao | 0% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T
|  |  | 2018-02-14 | 2018-02-23 | TBD | Bao | 0% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T
Firmware
|  |  | 2018-04-05 | 2018-04-08 | TBD | Bao | 0% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T
|  |  | 2018-04-08 | 2018-04-10 | TBD | Bao | 0% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T
|  |  | 2018-04-11 | 2018-04-16 | TBD | Bao | 0% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T
|  |  | 2018-04-14 | 2018-04-18 | TBD | Bao | 0% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T
|  |  | 2018-03-17 | 2018-03-21 | TBD | Bao | 0% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T
|  |  | 2018-03-20 | 2018-03-25 | TBD | Bao | 0% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T
eCAD Remote Controller
|  |  | 2018-04-05 | 2018-04-08 | TBD | Thomas | 0% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T
|  |  | 2018-04-08 | 2018-04-10 | TBD | Thomas | 0% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T
|  |  | 2018-04-11 | 2018-04-16 | TBD | Thomas | 0% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T
|  |  | 2018-04-14 | 2018-04-18 | TBD | Thomas | 0% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T
eCAD RF Transceivers
|  |  | 2018-04-05 | 2018-04-08 | TBD | Jon | 0% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T
|  |  | 2018-04-08 | 2018-04-10 | TBD | Jon | 0% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T
|  |  | 2018-04-11 | 2018-04-16 | TBD | Jon | 0% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T
|  |  | 2018-04-14 | 2018-04-18 | TBD | Jon | 0% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T
eCAD Power System Architecture
|  |  | 2018-03-05 | 2018-03-08 | TBD | TBD | 0% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T
|  |  | 2018-03-08 | 2018-03-13 | TBD | TBD | 0% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T
|  |  | 2018-03-11 | 2018-03-16 | TBD | TBD | 0% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T
|  |  | 2018-03-14 | 2018-03-19 | TBD | TBD | 0% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T
|  |  | 2018-03-17 | 2018-03-21 | TBD | TBD | 0% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T
|  |  | 2018-03-20 | 2018-03-25 | TBD | TBD | 0% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T
Example
|  |  | 2025-01-05 | 2025-01-06 | 1 | Alpha | 100% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T
|  |  | 2025-01-07 | 2025-01-08 | 2 | Bravo | 80% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T
|  |  | 2025-01-09 | 2025-01-13 | 3 | Charlie | 60% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T
|  |  | 2025-01-14 | 2025-01-17 | 4 | Delta | 40% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T
|  |  | 2025-01-18 | 2025-01-24 | 5 | Echo | 20% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T
|  |  | 2025-01-25 | 2025-02-03 | 6 | Foxtrot | 10% | bar: WEEK 2: 11/10 - 11/16 M to WEEK 2: 11/10 - 11/16 T
Formulas:
DURATION = NETWORKDAYS([START DATE],[END DATE])